## Product Backlog
THE APPLICATION DEVELOPMENT PROJECT TOPIC
PRODUCT BACKLOG
| TOTAL LOC |  | 3600 | Note: Total LOC should be >= 900 * Number of project members
Function Name | Feature | Complexity | LOC | Planned Code Iteration | Student No | In-charge Full Name | Actual Code Iteration | SRS Status | Design Status | Coding Status | Testing Status | % Completed | Completed in Iteration
Login | Common | Simple | 100 | Iteration 1 | SE05390 | Lê Trung Đức | Iteration 1 | Pending | Pending | Completed | Completed | 80% | Final
Register | Common | Simple | 100 | Iteration 1 | SE05390 | Lê Trung Đức | Iteration 1 | Pending | Pending | Completed | Completed | 80% | Final
Reset password | Customer | Simple | 100 | Iteration 4 | SE05390 | Lê Trung Đức | Iteration 4 | Pending | Pending | Completed | Completed | 80% | Final
Home page | Customer | Complex | 300 | Iteration 2 | SE05390 | Lê Trung Đức | Iteration 2 | Pending | Pending | Completed | Completed | 80% | Final
List car | Customer | Medium | 200 | Iteration 2 | SE05390 | Lê Trung Đức | Iteration 2 | Pending | Pending | Completed | Completed | 80% | Final
Car detail | Customer | Medium | 200 | Iteration 2 | HE151167 | Nguyễn Trí Trường Sơn | Iteration 2 | Pending | Pending | Completed | Completed | 80% | Final
User profile | Customer | Medium | 200 | Iteration 4 | HE151167 | Nguyễn Trí Trường Sơn | Iteration 4 | Pending | Pending | Completed | Completed | 80% | Final
My History Rental | Customer | Medium | 200 | Iteration 4 | SE05390 | Lê Trung Đức | Iteration 4 | Pending | Pending | Completed | Completed | 80% | Final
History Rental Detail | Customer | Medium | 200 | Iteration 4 | HE151166 | Nguyễn Hữu Minh Đức | Iteration 1 | Pending | Pending | Completed | Completed | 80% | Final
Dashboard(Admin) | Admin | Complex | 300 | Iteration 1 | HE151167 | Nguyễn Trí Trường Sơn | Iteration 1 | Pending | Pending | Completed | Completed | 80% | Final
List Car (Admin) | Admin | Medium | 200 | Iteration 1 | HE151166 | Nguyễn Hữu Minh Đức | Iteration 1 | Pending | Pending | Completed | Completed | 80% | Final
Car Detail (Admin) | Admin | Medium | 200 | Iteration 1 | HE151166 | Nguyễn Hữu Minh Đức | Iteration 1 | Pending | Pending | Completed | Completed | 80% | Final
List location (Admin) | Admin | Medium | 200 | Iteration 1 | HE151166 | Nguyễn Hữu Minh Đức | Iteration 1 | Pending | Pending | Completed | Completed | 80% | Final
Location Detail (Admin) | Admin | Medium | 200 | Iteration 1 | HE151166 | Nguyễn Hữu Minh Đức | Iteration 1 | Pending | Pending | Completed | Completed | 80% | Final
List User (Admin) | Admin | Medium | 200 | Iteration 3 | SE05390 | Lê Trung Đức | Iteration 3 | Pending | Pending | Completed | Completed | 80% | Final
User detail (Admin) | Admin | Medium | 200 | Iteration 3 | HE151166 | Nguyễn Hữu Minh Đức | Iteration 3 | Pending | Pending | Completed | Completed | 80% | Final
List Rental(Admin) | Admin | Medium | 200 | Iteration 4 | HE151167 | Nguyễn Trí Trường Sơn | Iteration 4 | Pending | Pending | Completed | Completed | 80% | Final
Rental detail (Admin) | Admin | Complex | 300 | Iteration 4 | HE151167 | Nguyễn Trí Trường Sơn | Iteration 4 | Pending | Pending | Completed | Completed | 80% | Final